## Sheet1
SAMPLE GRANT PROJECT
Studying the effects of X on Y
Robert Carden, PhD
Virginia Blood Foundation
| 1st quarter milestones/budget -- March 31, 2016 | Budget | Actual
| Purchase laptop | 1000
| Principal Investigator salary -- develop research question and hypothesis | 1000
| Research Assistant salary -- literature review | 500
| QUARTER TOTAL | 2500
2nd quarter milestones/budget -- June 30, 2016
| Principal Investigator salary -- develop research design | 1000
| Lab tech salary -- Obtain samples of X and Y | 500
| QUARTER TOTAL | 1500
3rd quarter milestones/budget -- September 30, 2016
| Lab tech salary -- Mix X & Y together and record results | 1000
| Principal Investigator salary -- supervision | 500
| QUARTER TOTAL | 1500
4th quarter milestones/budget --- December 31, 2016
| Statistician -- hypothesis testing and results | 1000
| Principal Investigator salary -- final report | 1000
| QUARTER TOTAL | 2000
| TOTAL PROJECT BUDGET | 7500